## bugs
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2024-02-15 | Sherry | P3 | resolved |  | When resizing the window, the screen boundry gets messed up and the scale of characters seems to change with the window size | Player stops at the edge of the screen | Player stops way before the edge | Resize window
Try to move to screen boundary
2 | 2024-02-13 | Tracy | P0 | Resolved | Ivena | Continuously switching between overworld & battle screens causes game to segfault | Continuously clicking the 'C' key to manually switch between screens will render the different screens as needed | Clicking ‘C' more than 2 times causes some sprites to render on the wrong screen, and clicking 'C’ about 2 more times will cause a segfault | Launch game
Click 'C' at least 4 times
3 | 2024-02-16 | Keelan | P2 | resolved | Tracy | Player position is erroneously able to change during battle scene and after battle scene. | Player position should never change during/after battle scene. | Player position changes during battle scene if movement keys were still being held on scene transition. After battle scene, player’s velocity is still non-zero as well, and player can move without any keys being actively pressed down. | Hold down any combination of WASD.
Press C while keeping WASD keys pressed.
Press C again after a few seconds to observe changes in player position.
4 | 2024-02-29 | Ivena | P0 | Resolved | Tracy | Game crashes when running in debug (works in release) | Game should start and window should render | Nothing renders and there’s an assert failure | Run game with configuration set to Debug
5 | 2024-03-02 | Keelan | P4 | Open | Keelan | Miss SFX sometimes does not play if too many happen | Every time a player presses a key where there is no collision, a miss SFX should play | If player misses many notes, then no miss SFX will play after about, maybe due to SDL channel limitations | Spam all DFJK keys rapidly, and notice that there are intervals where no miss SFX will play
6 | 2024-03-03 | Sherry | P4 | Resolved | Sherry | Walking animation stops when 2 keys are pressed down at the same time | Animation continues as usual | Walking animation is paused and sometimes resumes jerkily | Hold down a direction key (WASD)
While holding down that key press and hold another direction key
7 | 2024-03-02 | Keelan | P2 | Resolved (Collect all collisions first, then remove only the lowest note in each lane) | Keelan | Single key press can trigger two collisions at same time | When there are two notes colliding with the same judgment line, only the lowest one should be removed on player input. | All notes colliding with judgment line at the time of player input will be removed. | Most easily reproduceable in enemy1 (second battle) due to notes in quick succession.
Wait for opportunity where there are two notes close together in the same lane. Time the appropriate DFJK input when both notes are colliding with the judgment line.
8 | 2024-03-04 | Tracy | P4 | Resolved | Arianna | After entering battle by collision, when the battle over pop up appears, it renders behind the notes | Pop up should render over all on-screen entities | Pop up renders behind falling notes and sprite portraits in battle screen | Enter a battle by collision and either trigger or wait for battle end
9 | 2024-03-19 | Keelan | P0 | Resolved Added more guards in code. May have been due to key presses being a callback (?), and entities being removed unexpectedly. | Keelan | Crash on C key in battle scene. | Game should never crash during battle scene on any key press. | Game sometimes crashes during battle on pressing C key. | When pressing C when 3 or more notes are on screen (now with particles), game will crash. *Seems to be related to deleting generators in render_system.cpp. Commenting out prevents crashes but will cause memory leak.
10 | 2024-03-24 | Keelan | P2 | Resolved (Dummy spark-particle entities were not being removed from registry after effect expired) | Keelan | Game lags when many notes are on screen | Game should run smoothly even when many notes are on screen. | Game lags in battle scene when many notes are on screen. | Most noticeable in the middle of level 2. Simply watch the FPS counter drop over time
11 | 2024-03-24 | Keelan | P5 | Resolved (Unused particle data in memory had default colour of 1.f; set it to 0.f instead) | Keelan | Tiny particle(s) in top left corner | No particles should appear in top left corner in battle scene | There are tiny particles with unchanging values in the top left corner of battle scene | Enter battle scene
12 | 2024-03-26 | Tracy | P2 | Resolved | Tracy | Game not loading properly after saving a finished game | Game should start a new game if saved game is finished | Nothing gets rendered on screen after clicking "Load" on start screen | Have a saved game where player level = 4 and gameIsOver = true. Launch game and click "Load" in start screen
13 | 2024-03-26 | Tracy | P2 | Resolved | Tracy | Game not restarting as expected after colliding with high level enemy | New game should be started after clicking "New game" in start screen | Player is taken directly back to game over screen. New game doesn't start | Player enters the game over screen after colliding with high level enemy. Pressing SPACE key takes player back to the start screen. Clicking the "New game" button starts a new game
14 | 2024-03-24 | Keelan | P4 | Open |  | FPS may drop due to text-rendering taking particularly long (relative to other game loop steps). | FPS should remain above 60 at all times | FPS drops proportionally to the amount of text on screen | *Experienced on Mac M2, but not Windows PC. Play game, watch FPS counter. Uncomment profiling code in render_system.cpp to see runtimes measured in ms. Not a huge problem right now since our text is limited, and lowest FPS is during static moments (battle-over screen). But it will be a bottleneck if we add more in battle scene especially
15 | 2024-03-26 | Sherry | P4 | Open |  | Character portrait scale discrepancy | Scale of assets to be the same | Scale of assets is different and may be bigger or smaller depending on the screen | Open game, go to cutscene on 2 different resolution monitors

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release